## Slide 1: O2 (1/3)
V1.6 (Feb-17) | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
O2 TDR approved |  |  |  |  |  | 
Software process (6/16) |  |  |  |  |  | 
DDS release (6/16) |  |  |  |  |  | 
CCDB prototype (12/16) |  |  |  |  |  | 
DQM prototype (12/16) |  |  |  |  |  | 
CM prototype (6/17) |  |  |  |  |  | 
Control prototype (4/17) |  |  |  |  |  | 
First ALFA release (6/17) |  |  |  |  |  | 
Detector read-out DDL + GBT CRORC (12/16) |  |  |  |  |  | 
Detector read-out GBT CRU (6/17) |  |  |  |  |  | 
CCM: Control, Configuration & Monitoring DDS: Dynamic Distribution System
CCDB: Condition & Calibration Data Base DQM: Data Quality Monitoring

## Slide 2: O2 (2/3)
V1.6 (Feb-17) | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
Test time frame (5/17) |  |  |  |  |  | 
ITS and TPC in simulation framework (6/17) |  |  |  |  |  | 
Reconstruction for ITS and TPC (12/17) |  |  |  |  |  | 
Simulation for all detectors in O2 (12/17) |  |  |  |  |  | 
Calibration framework prototype (6/18) |  |  |  |  |  | 
Reconstruction for all detectors in O2 (6/18) |  |  |  |  |  | 
Simulation challenge (6/19) |  |  |  |  |  | 
10% data challenge (12/19) |  |  |  |  |  | 

## Slide 3: O2 (3/3)
V1.6 (Feb-17) | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
Definition of cooling system + EDR (3/17) |  |  |  |  |  | 
CR0 infrastructure ready (9/18) |  |  |  |  |  | 
Detector read-out (FLP) procurement (3/18) |  |  |  |  |  | 
Detector Read-out (FLP) installation (1/19) |  |  |  |  |  | 
Procurement 10% data processing and storage (12/18) |  |  |  |  |  | 
Installation 10% data processing and storage (9/19) |  |  |  |  |  | 
Procurement 90% data processing and storage (3/20) |  |  |  |  |  | 
Installation 90% data processing and storage (11/20) |  |  |  |  |  | 
LS2 |  |  |  |  |  | 
15 months contingency
pp data taking
10 months contingency
PbPb data taking